## Sheet1
Issues/Comments on DSWG specification
| Submitted | Submit
Num. | By | Date | Status | Issue | Disposition/Comments
1 | SD | 2004-08-23 | Closed | party/partyName should be required | Enforce in schema via redefine or in validation rules.
2 | SD | 2004-08-23 | Closed | party/partyId should be optional | Schema can't be changed; provider could supply null value
3 | SD | 2004-08-23 | Closed | there should be 2 parties | Put in minimum of 2. We should allow > 2 parties to support multiple legal entities in same feed, e.g. when dealer trades under multiple names
4 | SD | 2004-08-23 | Closed | positionSummary should be required | changed dswg schema to eliminate optionality
5 | SD | 2004-08-23 | Closed | positionHeader/tradeDate should be required | changed dswg schema to eliminate optionality
6 | SD | 2004-08-23 | Closed | positionHeader/receiverPositionIdentifier should be required | We can easily make this mandatory but will this always be available to the sender? Action: warn in XSLT if not provided
7 | SD | 2004-08-23 | Closed | why was "event" added? | It was added to allow specific calculated dates to be recorded, e.g. next reset date, when there is nowhere else in the schema to hold them. It has nothing to do with credit events or trade lifecycle events. I will adopt different naming for this type per GS suggestions.
8 | SD | 2004-08-23 | Closed | date adjustments on Calculation Period Dates not required due to master confirm | Does this apply to IR swaps? In any event, we cannot change this easily in the FpML schema; if the information is not relevent because it's covered by master confirm, business day convention should be "NotApplicable"; business centers could be left empty if they are required fields
9 | SD | 2004-08-23 | Closed | dummy values for fixing dates structure | will define what values to use if data can't be provided by sender; I don't recommend telling senders NOT to send this data.
10 | SD | 2004-08-23 | Closed | reset dates should be required for floating streams | Implement rule in XSLT
11 | SD | 2004-08-23 | Closed | initialRate should be required. | Leave initial rate optional for the initial rate, use a different rate for subsequent fixings.
12 | SD | 2004-08-23 | Closed | cancellableProvision | This is an aspect of the trade economics and typically has an effect on valuation; recommend retaining this structure.
13 | SD | 2004-08-23 | Closed | extendibleProvision not required | We could prohibit this but it's unclear what the benefit would be. Recommend retaining this.
14 | SD | 2004-08-23 | Closed | settlementRateOptions should be required. | This doesn't appear to be relevant when FX conversion is not required; SD to clarify comment.
15 | SD | 2004-08-23 | Closed | stream events (scheduled dates) should be required | Yes, this will be addressed by validation xslt.
16 | SD | 2004-08-23 | Closed | specific valuations should be required. | Yes, this will be addressed by validation xslt.
17 | SD | 2004-08-23 | Pending | source for settlementRateOption values | ISDA publishes a list - it's in the appendix to the user's guide to the 1998 FX definitions, I believe. It's not currently in XML form but they might convert it if we ask nicely. Action: ask ISDA, otherwise publish own scheme.
18 | SD | 2004-08-23 | Closed | clarification on "event/type" purpose. | This holds calculated dates during the lifetime of the deal, e.g. next reset date, previous reset date.
19 | SD | 2004-08-23 | Closed | Collateral items (independent amount, percentage, etc.) should be required. | Warn in XSLT if not provided
20 | SD | 2004-08-23 | Closed | Collateral calculation method is what? | Delete this, not required at the moment
21 | SD | 2004-08-23 | Closed | TRS relative dates | Addressed by validation XSLT
22 | SD | 2004-08-23 | Closed | Cusip is always required for US securities, ISIN or SEDOL for non-US. | To be addressed by validation XSLT. Domestic security will be determined based on the exchange.
23 | SD | 2004-08-23 | Closed | exhangeID should be required | To be addressed by validation XSLT - done for equities only.
24 | SD | 2004-08-23 | Closed | underlyingAsset Currency should be required | To be addressed by validation XSLT.
25 | SD | 2004-08-23 | Closed | Instrument type should be provided. | This is provided by the tag name of the specific underlying security (e.g. "bond", "equity", etc.)
26 | SD | 2004-08-23 | Closed | dividendPayoutRatio choice should be required | To be addressed by validation XSLT.
27 | SD | 2004-08-23 | Closed | For baskets, open units for entire basket should be optional, open units and weight for each basket constituent is required. | FpML schema defines this info at the constituent level. If necessary, open units for the entire basket could be calculated from the constitutent data.
28 | SD | 2004-08-23 | Closed | Specify precision for basket percentage. | Should be 6
29 | SD | 2004-08-23 | Closed | commissionDenomination needs to be specified | FpML defines an enum: BPS, Percentage, CentsPerShare, FixedAmount. Unless there is a problem with this, this appears to be covered.
30 | SD | 2004-08-23 | Closed | Review definition of gross/clean | FpML uses gross/net to refer to including/excluding commissions; this is independent of accrued interest. In FpML, the net price is defined as excluding commissions but INCLUDING accrued interest, i.e. it is a dirty price.
31 | HBK | 2004-08-24 | Pending | Additional day counts required | FpML has agreed to convert the current enumeration back to a scheme to accommodate our needs. We need to provide more detail on the requested day counts so that FpML can consider adding them to the standard FpML scheme.
32 | HBK | 2004-08-24 | Closed | Floating rate components should be required, not optional. | Change not required
33 | HBK | 2004-08-24 | Closed | AdjustedPaymentDate shouldn't be used, rather unadjusted | Change not required
34 | HBK | 2004-08-24 | Closed | EquityBermudaExercise - expiration time should be mandatory. | Currently out of scope
35 | HBK | 2004-08-24 | Closed | make dividendAmount and Payment Date "more mandatory", but data isn't always available. | add "warnings" to the XSL validation. (This element holds the rule, not the dates/amounts - should we be checking the dates/amounts?)
36 | HBK | 2004-08-24 | Closed | EquitySwap - capable of handling debt? | We believe that it should be, as the underlying instrument can be a debt instrument, although we may need to make a few additions/enhancements. However, we will need to produce a couple of good examples to confirm this. It's likely that during implementation some additional issues will come up.
37 | HBK | 2004-08-24 | Closed | EquitySwapValuationPrice - commission should be mandatory (even if 0) | This can be done by redefining the FpML schema or adding to validation rules.
38 | HBK | 2004-08-24 | Closed | Index Tenor should be mandatory in Floating Rate Calculation | This is optional in part because tenor doesn’t really apply for certain instruments (e.g. OIS). Suggest that we write an XSLT warning, perhaps later consider enhancing it so that it doesn't warn if the trade is an OIS.
39 | HBK | 2004-08-24 | Complete | ProductType and ProductId should be mandatory | Make this tested in the validation scripts
40 | HBK | 2004-08-24 | Closed | feeLeg payment info should be mandatory. | Warn if nothing filled in (at least one must be present)
41 | HBK | 2004-08-24 | Pending | identification of Indices (for CDS) | FpML does not currently define a set of scheme values. Sent note to Ben Lis, chair of FpML CDWG, to determine if FpML will publish a list. We will probably need to define a scheme.
42 | HBK | 2004-08-24 | Closed | NotDomesticCurrency should be required even if USD | Need to review meaning of this field - I believe it has specific confirmation significance; it may be incorrect to require it always; I think that the currency of the CDS itself is defined elsewhere. Action: BDF to review comment, determine if still open.
43 | GS | 2004-08-26 | Closed | Can base currencies other than USD be specified in "quotationCharacteristics" | Yes, that is the intention.
44 | GS | 2004-08-26 | Closed | Should quotationCharacteristics be limited, e.g. through documentation | Add ability to specify quotation characteristics per position. Limit this field through documentation and through XSLT warnings.
45 | GS | 2004-08-26 | Closed | ProductType and ProductId are difficult to populate. | Algorithm implemented in XSLT - to be documented
46 | GS | 2004-08-26 | Closed | StreamEvents - rename to scheduled Dates | This is a good suggestions; I will look at using names based on this idea to clarify the schema.
47 | GS | 2004-08-26 | Closed | Stream Events type based on a scheme for tighter control | We could do this, but we can achieve a similar effect using XSLT validation rules to ensure that the appropriate values are provided. This will be more flexible than an enumeration but ensure that the values are validated.
48 | GS | 2004-08-26 | Closed | Measure type based on a scheme for tighter control | We could do this, but we can achieve a similar effect using XSLT validation rules to ensure that the appropriate values are provided. This will be more flexible than an enumeration but ensure that the values are validated.
49 | GS | 2004-08-26 | Closed | CDS/TRS security Identifiers needed should be specified | This comment is similar to SD's issue #22 - yes, we can provide this info.
50 | GS | 2004-08-26 | Closed | TRS commissions - clarify | Provide example based on Brian Weigus's example. Commissions do not record the total paid during the life of the trades. Commissions are not impacted by equity reset events. Commission per trade is commission to close out the remaining position.
51 | GS | 2004-08-26 | Closed | TRS commissions - difference by underlyer | In FpML, commissions may be specified per underlying by supplying the "underlyerPrice" element in "BasketConsituent". DSWG requests that this information be provided.
52 | GS | 2004-08-26 | Closed | Proposal for handling of reset price vs. initial price | Add "initialPrice" and "currentMarketPrice" to BasketConstituent to allow this information to be captured.
53 | GS | 2004-08-26 | Closed | Dirty vs. clean price mapped to Net and Gross price | This appears to be an error in my interpretation of the FpML specification; need to confirm and resolve in the schema.
54 | GS | 2004-08-26 | Closed | Is it necessary to specify both clean and dirty price if accrued interest is specified? | For size and complexity reasons, we agree that it is acceptable to just specify accrued interest. Need to address latest reset vs. current price
55 | GS | 2004-08-26 | Closed | Number of Underlying Securities | Number of underlying securities will be done by multiplying par value times open units | agreed
56 | GS | 2004-08-26 | Closed | Location of dividend settlement date (for multiple underlyers) | Added "scheduled dates" element to basket constituent
57 | GS | 2004-08-26 | Closed | CDS - interest accrual should be supported | Listed as a required valuation type
58 | GS | 2004-08-26 | Closed | TRS - location of data related to multiple underlyers (accruals, etc.) | Added "valuations" element to basket constituent
59 | GS | 2004-09-15 | Closed | scheduledDates - documentation still refers in places to events
60 | GS | 2004-09-15 | Closed | scheduledDates - need to update cross reference
61 | GS | 2004-09-15 | Closed | product typology - swaps | clarify precedence rules
62 | GS | 2004-09-15 | Closed | product typology - swaptions | add underlying swap dimension
63 | GS | 2004-09-15 | Closed | product typology - TRS | this is basically what was proposed, will clarify
64 | GS | 2004-09-15 | Closed | scheduled date example issue | change the spreadsheet to indicate that these are required.
65 | GS | 2004-09-15 | Closed | handling of notionals for amortizing/accreting swaps | ok - new xpath expression for uneven notionals documented
66 | GS | 2004-09-15 | Closed | Current notional - is this required? | this can be removed, confirm not required, handled elsewhere
67 | GS | 2004-09-15 | Closed | Will TRSs with several underlyer CCYs be required? This will require adding an FX element | Multiple currencies are expected to be required; we've added an optional unbounded FxRate structure that can be used to hold the FX rates used for the conversions.
68 | GS | 2004-09-15 | Closed | update the cross reference for clean/dirty price
69 | GS | 2004-09-15 | Closed | clarify meaning of "last reset date" | Rename to "Previous"
70 | GS | 2004-09-15 | Closed | In the schema specification document, the table p. 24 indicates that the accruedCoupon will be reported at the leg level. On the other hand, p. 17 of the document it is indicated that the currentMarketPrice needs to be reported at the underlyer level (i.e. one value per underlyer). (BTW, this element is missing from the currentMarketPrice element is missing from the table p. 24 and should probably be added.) If we understand correctly that the accruedCoupon is the interest component of the dirty bond price at a point in time (excerpt from the specification spreadsheet: “Accrued Coupon on underlying (if applicable) from last coupon pay date to As of Date”), shouldn’t it be represented through the currentMarketPrice/ accruedInterestPrice element, i.e. at the underlyer level in the case of basket swaps? | Clarify meaning of table on p. 24. Eliminate "AccruedCoupon" and "AccruedBondCoupon" from the list of measures as redundant and not required.
71 | GS | 2004-09-15 | Closed | Representation of pending dividend/coupon information | Implemented
72 | GS | 2004-09-15 | Rejected | Policy question on which price information to provide -> requested mapping change | It is acceptable not to provide initial price for short term implementations, but the proposed changed in tag meaning is not accepted.
73 | GS | 2004-09-15 | Closed | Provide example and mapping info at basket underlyer level. | Provided
74 | GS | 2004-10-17 | Closed | The schema specification document, page 26, indicates that for the total return swap the reset dates should be both at the leg and the basket constituent level. This appears to be an error. | updated table and removed "scheduledDates" optional component from the schema.
75 | GS | 2004-10-18 | Closed | FX rate for NPV conversion | correct - add FX rates to valuation structure. Need to add to example.
76 | DSWG | 2004-10-19 | Closed | Update FpML version to LCWD | need to validate against examples
77 | DSWG | 2004-10-19 | Closed | Incorporate FpML collateral info | updated spec, examples, cross reference
78 | GS | 2004-10-20 | Closed | Commission Per Trade - update? | no change
79 | GS | 2004-10-20 | Closed | Page 25 - The spec is missing the indication of the market value of the underlyer (rows 28 and 29 of the spreadsheet). As discussed, these would be at the underlyer level. | Add as an optional field. In progress … need to clarify definition (clean/dirty, net/gross)
80 | GS | 2004-10-20 | Rejected | If this understanding is correct, you may also want to consider whether the accrued coupon should not be implied from one of these values. (If we provide both the clean and the dirty price, is there also a need for the accrued coupon portion of the dirty price?) | Don't want to compute anything.
81 | DSWG | 2004-10-21 | Closed | incorporate changes for pricing | added underlyingAsset price to singleUnderlyer; updated xref and example
82 | DSWG | 2004-10-21 | Closed | initial price vs. latest reset price | update example
83 | DSWG | 2004-10-22 | Closed | fix errors in examples; add TRS with a bond underlyer | removed swaption, added TRS on bonds (but still needs some work).
84 | GS | 2004-10-26 | Closed | realized trading gains | Provide independently for each leg - FundingOnRealizedGains? Implemented, but pending confirmation from SD.
85 | DSWG | 2004-10-26 | Closed | change uri to be based on "datastandardsworkinggroup.org" | Change implemented in doc, schema, examples, and validation script.
86 | DSWG | 2004-10-29 | Closed | clean vs dirty price - dswg wants both | updated schema, doc, examples, xref
87 | DSWG | 2004-10-29 | Closed | product id - update documentation | Documentation update - sender to provide product id
88 | DSWG | 2004-10-29 | Closed | sign issue on quantity - update documentation, and examples | Document that open units may be negative, and provide an example.
89 | BAL | 2004-11-02 | Closed | mapping of TRS effective date to interestLeg is a problem, because interest leg is optional | change mapping to equity leg.
90 | DSWG | 2004-11-02 | Closed | CDS product description refinements | Changed product description to require "CDS-U" or "CDS-S" for US or Sovereign, and updated xref, validation, and examples to follow. Pending confirmation from DSWG.
91 | BAL | 2004-11-05 | Closed | Additional payment - cross reference not specific enough | Additional payment - refine cross reference, add example
92 | BAL | 2004-11-05 | Closed | validation scripts don't detect extra valuation measures, some missing measures | update to correct.
93 | BAL | 2004-11-05 | Open | examples with nonmeaningful data | somewhat improved, still open - too large to do in a reasonable time
94 | BAL | 2004-11-05 | Closed | inconsistent example indentation | run tidy
95 | BAL | 2004-11-05 | Closed | Number of Underlying Securities is calculated - is this a problem? | added numberOfUnderlyingSecurities to schema
96 | DSWG | 2004-11-09 | Closed | FinalPayment date for TRS - is it really needed? At what level? | Have a single FinalPayment date at the equity swap level
97 | DSWG | 2004-11-10 | Closed | Haircut vs. payout ratio | add dividendHaircutRatio, updated example, validation, xref - updated xref to use SD's proposed naming; ratained existing naming in FpML/DSWG.
98 | DSWG | 2004-11-11 | Closed | Not all fields are validated | most fields are now validated. Need to review remaining fields with SD/PM.
99 | GS | 2004-11-29 | Complete | remove haircut | update documentation, example.
100 | DSWG | 2004-11-29 | Complete | change percentages to 0.85 | update documentation, example, validation
101 | DSWG | 2004-11-29 | Complete | allow any underlying type | remove error message for unknown underlying types.
102 | GS | 2004-11-29 | Complete | validation limitation in v.0.6 scheduled dates | add more detail to message
103 | Barclays | 2004-11-29 | Closed | Should validation complain about a default quotation currency of "JPY"? | This message is provided to notify the recipient when a provider sends valuations in a non-preferred currency. NPV in local currency should specify the local currency explicitly. View is that this message is a legitimate warning for the sample file.
104 | DSWG | 2004-12-03 | Complete | Add additional validation rules | Added about 10 new validation rules or enhancements.
105 | GEM | 2004-12-03 | Complete | some mappings in Excel xref don't exactly match example/spec | A number of inconsistencies identified by GEM but not yet incorporated,plus additional examples reported by Paul Riley.
106 | GS | 2005-12-15 | Complete | realized trading gains in validator | Spec requires these only at leg level; example and validator have this at the underlyer level (affects rules DSWG.010 and DSWG.011)
107 | GS | 2004-12-24 | Complete | collateral validation not tight enough | The validator currently requires that only one of the independent amount or the independent percentage to be provided. I think that you are right and that the independent amount should be required explicitly. This appears to be an oversight. Will correct once we confirm.
108 | GS | 2004-12-24 | Complete | Product type code wrong for convertible bonds in validator | From GS: (DSWG.041) supplied product type (TRS-ConvertibleBond-Single-EarlyTerm) does not match expected value (TRS-Convert-Single-EarlyTerm). Our code seems to be matching the specification document (page 23): the abbreviation in the exception stylesheets seems to be the part that requires and adjustment (no abbreviation).
109 | DSWG | 2/7/2005 | Complete | Add "error" prefix to all validation errors. | To simplify analysis of results.
110 | DSWG | 2005-02-16 | Complete | "cleanNet" vs "netClean" Price | Error in xref, TRS row 21
111 | DSWG | 2005-04-01 | Complete | Change asset swap option representation to have variable strike
112 | DSWG | 2005-05-13 | Complete | Generalize USD market value to reporting CCY market value | Change name of field in xref to support non-USD reporting currencies. Add reporting currency field to xref. Warn if reporting CCY not specified.
113 | DSWG | 2005-05-13 | Complete | Clarify direction of NPV | Positive value means in favor of fund (recipient). Add documentation. Add the ability to specify multiple base parties in a position report message. Clarify comment on local MTM in FX fwd/option - different wording from DSWG comment.
114 | DSWG | 2005-05-13 | Complete | Swaption Expiration Xpath | Feedback that path may be wrong - add comment explaining the Xpath.
115 | DSWG | 2005-05-13 | Complete | CDS interest accrual start date | Usually same as effective date. Add to documentation of required scheduled dates, to XREF, to validation script, and example.
116 | DSWG | 2005-05-13 | Complete | Var Swap Cash/Futures Indicator | Clarify value - "cash" or "futures" - update comment in XREF, change spelling to "Futures" from "Future".
117 | DSWG | 2005-05-13 | Closed | Var Swap dividend treatment | Enumeration values clarified
118 | DSWG | 2005-05-13 | Complete | Var swap - add notional ccy | new field in xref; already in schema/example.
119 | DSWG | 2005-05-13 | Complete | Asset Swap Opt: Make Whole Xpath | correct xpaths for make-whole provisions as commented (remove erroneous "fpml:exercise").
120 | DSWG | 2005-05-13 | Complete | CCY Fwd Settle Date Xpath | remove reference to non-deliverable ccy settlement date.
121 | DSWG | 2005-05-13 | Complete | CCY Opt Exercise exp date/time xpath | change "$prod" to "$opt"
122 | DSWG | 2005-05-13 | Closed | CCY Opt Exercise detail | Added FxBermudaExpiry type and validation rule 521.
123 | DSWG | 2005-05-13 | Closed | CDS pmt day count | Duplicate of existing field
124 | DSWG | 2005-05-13 | Complete | Additional Swaption field | Add expiration time to Swaptions - add to XREF; already present in schema
125 | DSWG | 2005-05-13 | Closed | FX positions | In the FX market, the determination of initial collateral is sometimes done currency position by currency position, not trade by trade. Create a level of position aggregation by currency that is consistent with the industry practice. Allow independent amount, CCY and % for FX products to be specified at the trade or aggregation level. Adjust validation rules and documentation to support this.
126 | DSWG | 2005-05-13 | Closed | Precision | Specify 8 decimals for rates, 2 for currency amounts. Perform validation testing. Mostly complete; pending some feedback.
127 | DSWG | 2005-05-13 | Closed | Percentages as decimal | Add validation rules for rates.
128 | DSWG | 2005-05-13 | Complete | Valuation direction | Report accruals from client perspective not Dealer. - updated documentation; examples.
129 | DSWG | 2005-05-13 | Complete | XREF - more detail in Xpaths | Expand attribute document to include XREF variable names to the full path - replaced all variables with complete paths.
130 | DSWG | 2005-05-13 | Closed | Floating Rate index values | Add validation rules to ensure that underscores are not used.
131 | DSWG | 2005-05-13 | Closed | Documentation of unavailable data items | Use "N/A" rather than empty for unavailable data.
132 | DSWG | 2005-05-13 | Closed | Specify File naming convention: | Provided per DSWG comments.
133 | DSWG | 2005-05-13 | Complete | Doc typo, p. 7 | page. 7: ‘Total Request Swaps’ - corrected
134 | DSWG | 2005-05-13 | Complete | Doc typo, p. 33 | page 33: reference to the dswg:GenericOption, which has been commented out in the schema.
128 | DSWG | 2005-05-31 | Closed | Validate floating rate indexes | validate against a list from the annex to the isda 2000 definitions
129 | DSWG | 2005-05-31 | Closed | Example of basket option | provide example of an equity option on a basket and verify that validation rules and cross-references are ok.
130 | DSWG | 2005-06-09 | Complete | FX aggregation | Eliminate FX aggregation and replace with a simpler FX aggregate collateral construct.
131 | DSWG | 2005-06-09 | Complete | Clarify accrual ccy | Clarify in documentation that accruals, etc. should be in the local currency, not the reporting currency
132 | DSWG | 2005-06-09 | Complete | CDS on Baskets | add support for a CDS on a basket of underlyers.
133 | DSWG | 2005-07-05 | Complete | CDS on indexes | allow CDS indexes to be included in DSWG format files
134 | DSWG | 2005-07-27 | Complete | Short form product | add a product to cover all remaining product types
135 | GEM | 2005-08-18 | Complete | Xref errors | Some minor errors in XREFs - variance swaps had wrong product prefix (equitySwap instead of dswg:varianceSwap), plus a couple of typos.
136 | GEM | 2005-08-18 | Complete | EQO business center issues | Validation rules didn't require business centers for premium payment and expiration dates, and the examples didn't include them.
137 | GEM | 2005-09-07 | In progress | Correct xpaths | A number of xpaths in the field cross reference for 1.1 were found to be slightly incorrect during extractor development. Resolution: correct sheet
138 | GEM | 2005-09-07 | In progress | Extra fields for short form products | Extraction of the short form products into pay and receive information could not be done reliably with 1.1 schema - add new fields "senderPartyReference" an "receiverPartyReference"
139 | BofA | 2005-09-07 | Open | "previous reset" inconsistency | Docementation says that TRS "previous reset" is not required when no previous reset; validation requires it anyway; XLS asks for the initial value.
| Definition of statuses: |  |  | No decision has been taken on how to resolve the issue. Clarification, discussion, or further analysis is required.
We are waiting for an input from an outside group, e.g. FpML.
|  |  | Open | Agree with comment, but issue remains to needs to be addressed.
|  |  | Pending | Propose a different way to resolve issue.
|  |  | Agreed | Proposal not accepted
|  |  | AlternativeSolution | The proposed change has been incorporated, or no change is required.
Rejected
Closed